## Sheet1
Time Estimate for Project Name
SL No | Project | Phase | Project Module | Project Sub Module | Progress | Hours Total 50 | Start Date | End Date | Proposed End Date | Status
1 | Pet Care System | Design Phase | User | Login | Login Page contains username and password with a login button that helps to log into the application on the user side | 1 | 2022-07-25 | 2022-07-25 |  | Completed
2 | Pet Care System | Design Phase | User | Registration |  | 1 | 2022-07-25 | 2022-07-25 |  | Completed
3 | Pet Care System | Design Phase | Admin | Add Question |  | 1 | 2022-06-15 | 2022-06-15
4 | Pet Care System | Design Phase | Admin | Add Course |  | 1 | 2022-06-16 | 2022-06-16
5 | Pet Care System | Design Phase | Admin | View Mark |  | 1 | 2022-06-17 | 2022-06-17
6 | Pet Care System | Design Phase | Admin | About/ Contact us |  | 1 | 2022-06-18 | 2022-06-18
7 | Pet Care System | Design Phase | Admin | LogOut |  | 1 | 2022-06-19 | 2022-06-19
8 | Pet Care System | Design Phase | User | Login |  | 1 | 2022-06-19 | 2022-06-19
9 | Pet Care System | Design Phase | User | Home |  | 1 | 2022-06-19 | 2022-06-19
10 | Pet Care System | Design Phase | User | Register for Exam |  | 1 | 2022-06-20 | 2022-06-20
11 | Pet Care System | Design Phase | User | Result |  | 1 | 2022-06-21 | 2022-06-21
12 | Pet Care System | Design Phase | User | About/ Contact us |  | 1 | 2022-06-22 | 2022-06-22
13 | Pet Care System | Design Phase | User | LogOut |  | 1 | 2022-06-23 | 2022-06-23
1 | Pet Care System | Development Phase | Admin | Login |  | 2 | 2022-06-24 | 2022-06-24
2 | Pet Care System | Development Phase | Admin | Home |  | 2 | 2022-06-25 | 2022-06-25
3 | Pet Care System | Development Phase | Admin | Add Question |  | 2 | 2022-06-26 | 2022-06-26
4 | Pet Care System | Development Phase | Admin | Add Course |  | 2 | 2022-06-27 | 2022-06-27
5 | Pet Care System | Development Phase | Admin | View Mark |  | 2 | 2022-06-28 | 2022-06-28
6 | Pet Care System | Development Phase | Admin | About/ Contact us |  | 2 | 2022-06-29 | 2022-06-29
7 | Pet Care System | Development Phase | Admin | LogOut |  | 1 | 2022-06-30 | 2022-06-30
8 | Pet Care System | Development Phase | User | Login |  | 2 | 2022-07-01 | 2022-07-01
9 | Pet Care System | Development Phase | User | Home |  | 2 | 2022-07-02 | 2022-07-02
10 | Pet Care System | Development Phase | User | Register for Exam |  | 2 | 2022-07-03 | 2022-07-03
11 | Pet Care System | Development Phase | User | Result |  | 2 | 2022-07-04 | 2022-07-04
12 | Pet Care System | Development Phase | User | About/ Contact us |  | 2 | 2022-07-05 | 2022-07-05
13 | Pet Care System | Development Phase | User | LogOut |  | 1 | 2022-07-06 | 2022-07-06
1 | Pet Care System | Testing Phase | Admin | Login |  | 1 | 2022-07-07 | 2022-07-07
2 | Pet Care System | Testing Phase | Admin | Home |  | 1 | 2022-07-08 | 2022-07-08
3 | Pet Care System | Testing Phase | Admin | Add Question |  | 1 | 2022-07-09 | 2022-07-09
4 | Pet Care System | Testing Phase | Admin | Add Course |  | 1 | 2022-07-10 | 2022-07-10
5 | Pet Care System | Testing Phase | Admin | View Mark |  | 1 | 2022-07-11 | 2022-07-11
6 | Pet Care System | Testing Phase | Admin | About/ Contact us |  | 1 | 2022-07-12 | 2022-07-12
7 | Pet Care System | Testing Phase | Admin | LogOut |  | 1 | 2022-07-13 | 2022-07-13
8 | Pet Care System | Testing Phase | User | Login |  | 1 | 2022-07-14 | 2022-07-14
9 | Pet Care System | Testing Phase | User | Home |  | 1 | 2022-07-15 | 2022-07-15
10 | Pet Care System | Testing Phase | User | Register for Exam |  | 1 | 2022-07-16 | 2022-07-16
11 | Pet Care System | Testing Phase | User | Result |  | 1 | 2022-07-17 | 2022-07-17
12 | Pet Care System | Testing Phase | User | About/ Contact us |  | 1 | 2022-07-18 | 2022-07-18
13 | Pet Care System | Testing Phase | User | LogOut |  | 1 | 2022-07-19 | 2022-07-19